## Skillport 8
|  | Skillport 8 Implementation Project Plan |  | Target Launch to Users Date:
New | Upgrade | Task/Deliverables | Responsibility | # of Days Back | Planned End Date | Day of Week | Actual End Date | Comment | Notes/Links
x | x | Planning/General
x | x | Verify Books, ILT, Community/inGenius, Wikis, Blogs, KCs, Skillsoft Advantage, Live Learning , Custom Content Hosting (Publisher) are included in the agreement. If any of these add-ons are included, make certain to refer to the specific section/ worksheet as you work through SkillPort implementation. | LC | 40
x | x | Client must have valid contract for hosting | LC | 40
x | x | Register Customer for Client Community Access | LC | 37 |  |  |  |  | http://community.skillsoft.com/register.asp
x | x | Send customer link to product documentation | LC | 40 |  |  |  |  | http://documentation.skillsoft.com/en_us/skillport/8_0/ah/#48850.htm
| x | Review New Features and Upgrade considerations topic in the product documentation with customer | LC | 40 |  |  |  |  | http://documentation.skillsoft.com/en_US/Skillport/8_0/ah/index.htm#47799.htm
x |  | Send link to the Strategic Implementation Process - A Roadmap for Program Success and Business Impact | LC | 40 |  |  |  |  | http://skillsoft.com/implementation/
x |  | Send and Review Strategic Implementation Planning Guide/Worksheet Found on the Program Launch page on Client Community | LC/Customer | 40 |  |  |  | Make certain goals and measurement criteria have been set | https://community.skillsoft.com/marketing/programlaunch.asp
x | x | If appropriate, select courses and provide list to SkillSoft | Customer | 40 |  |  |  |  | https://community.skillsoft.com/ContentAdmin/
x | x | Develop Implementation Project Plan | LC/Customer | 37
x | x | Consult with AE regarding any Platform Customizations | LC | 40
x | x | Consult with AE regarding OLSA builds | LC | 40 |  |  |  | https:// recommended
x | x | Consult with AE regarding access from mobile devices | LC | 40 |  |  |  |  | Hosting has to install the RIA player in order for mobile content to play on smartphones and tablets.
x | x | Provide customer link to the Skillport 8 product demonstration | LC | 40 |  |  |  |  | http://cclibrary.skillport.com/custom/sccp/spskilltrain/web/content/sp8_demo_022013B.htm
x | x | Determine if site needs to be Akamized | LC | 40
x | x | Discuss completion criteria | LC/Customer | 40
x | x | Deployment and Technical Considerations
x | x | Review Skillport configuration options document | LC/Customer | 40 |  |  |  |  | This document will help you determine which features need to be enabled by Hosting.
x | x | Provide client with test script so they can determine if there are any connectivity issues | RAE, LC or PSG | 40 |  |  |  |  | https://sp.skillsoft.com/SalesSupport/Processes/Pages/Hosted-Services-Validation.aspx
x | x | Check the Knoweldge Base for Known Issues and Release Notes | LC | 40 |  |  |  |  | http://documentation.skillsoft.com/en_us/skillport/8_0/ah/index.htm#47785.htm
x | x | Submit approval requests to skillport8controlledrelease@skillsoft.com during controlled release period (all builds and upgrades) | LC | 38 |  |  |  |  | https://sp.skillsoft.com/Products/ControlledRelease/Documents/Skillport_8_Controlled_Release_Qualification_Form.docx
x | x | Review Site Customization Options | Customer | 35 |  |  |  |  | http://documentation.skillsoft.com/en_us/skillport/8_0/ah/index.htm#31195.htm
x | x | Preview Skillport Learner simulations - Getting Acquainted with Skillport 8 | Customer | 21 |  |  |  |  | http://documentation.skillsoft.com/en_us/skillport/8_0/ah/#48719.htm
| x | Review New Features topics in Knowledge Base (Admin) | Customer | 21 |  |  |  |  | http://documentation.skillsoft.com/en_us/skillport/8_0/ah/index.htm#47442.htm
| x | Review the New Features topic in the Knowledge Base (Learner) | Customer | 21 |  |  |  |  | http://documentation.skillsoft.com/en_us/skillport/8_0/ah/index.htm#47843.htm
x | x | Submit Build/Upgrade Request using PSG Online Request form | LC | 21 |  |  |  |  | Attach approval email from Product Marketing during controlled release period for all builds (new and upgrades).
| x | Review requirements to approve the build. | PSG | 21 |  |  |  |  | Confirm customer is contractually entitled to a Skillport iste and that the contractual entitlements will be valid at time of the upgrade
x | x | Develop/update Client Support Process - Review SOP for end user support with the Tier One Support team in Fredericton | Customer, LC, Darren MacPhee | 28 |  |  |  | Is client using Skillsoft Support or their own internal support (first line of support) | https://sp.skillsoft.com/Services/CustomerSupportServices/Pages/Home.aspx
x | x | Complete/update Technical Ref Notes for client and submit to %Customer Service Team Leads email distribution list | Customer, LC, Darren MacPhee | 28 |  |  |  |  | https://sp.skillsoft.com/Services/CustomerSupportServices/Pages/Home.aspx
x | x | Register for Skillport training OR complete elearing curriculum on Skilltrain (Client Community) | Customer | 21 |  |  |  |  | http://community.skillsoft.com/ProductTraining/SkillPortAdmin.asp
x | x | Send link for Skilport Adminstrator's Guide | PSG | 21 |  |  |  |  | http://documentation.skillsoft.com/en_us/skillport/8_0/print/sp_admin_guide_8.doc
x | x | Send Skillport templates, guides and graphics | PSG | 21
| x | Review current entitlements and catalog assignments (to determine how this will look in SP8) | LC/Customer | 21 |  |  |  |  | https://sp.skillsoft.com/Products/Skillsoft Product Documentation Library/Best_Practices_for_Using_Filters_in_Skillport8.docx
x | x | Work wth customer to understand and document browse views, featured topics, series, highlighted content, etc. (any customization to entitlements and views) | LC/Customer | 28 |  |  |  | Skillsoft LC can assist with curriculum consulting
x | x | Determine content entitlements and make appropriate assignments Create custom browse views, libraries, featured topics, series, etc. | Customer | 21 |  |  |  | With assistance from LC
x | x | Identify user profile fields (up to 30) | LC/Customer | 21 |  |  |  |  | http://documentation.skillsoft.com/en_us/skillport/8_0/ah/index.htm#47445.htm
x | x | Conduct the customization options call | PSG/DC | 21
x | x | Send Customization Summary Document | PSG | 21
x | x | Send company logo (electronic) and/or other graphics to personalize Skillport site to PSG | Customer | 21 |  |  |  |  | Login page image Banner logo What's New page image Custom images for content (i.e. Series and Learning program)
x | x | Send any changes or new content needed to customize the login page, template or content pages to PSG | Customer | 21
x | x | Identify/Review groups and users in batch file (Normal, Advanced and Assignment groups) | Customer | 21
x | x | Validate login page and any additional pages needed for site build and submit for installation | PSG | 21
x | x | Build web site for customer | Skillsoft Build Engineer | 10
x | x | Create user profile fields and determine where visible | PSG/LC/Customer | 10
x | x | Send/download Batch File templates | PSG/LC/Customer | 10
x | x | Complete batch file templates, submit and upload | PSG/LC/Customer | 10
x | x | Add groups and users with batch process | Skillsoft Build Engineer | 10
x | x | Release site for final review | PSG | 7
x | x | Conduct site walk through | PSG/Customer | 7
x | x | Complete Skillport Administrator Training (VILT or elearning) | Customer Administrator | 7
x | x | Complete any additional customizations to the site through the Administrative options | Customer Administrator | 3
x | x | Identify any needed keywords | Customer Administrator | 3
x | x | Create/review/update keywords in Skillport | Customer Administrator | 3 |  |  |  | Wait 24 hours for the search to reindex
x | x | Identify need for custom email notifications | Customer Administrator | 3
x | x | Create, activate and assign custom email tempates | Customer Administrator | 3
x | x | Turn off email notifications as appropriate | Customer Administrator | 3
x | x | Enable inGenius/Community | Customer Administrator | 3
x | x | Enable Wikis | Customer Administrator | 3
x | x | Enable Blogs | Customer Administrator | 3
x | x | Identify inGenius community Administrator(s) | Customer Administrator | 3
x | x | Assign inGenius community Administrator(s) in Skillport | Customer Administrator | 3
x | x | Identify Wiki roles (Community Admin(s), Contributors, Authors | Customer Administrator | 3
x | x | Identify Blog Roles (Community Admin(s), Contributors, Authors) | Customer Administrator | 3
x | x | Assign Wiki roles in Skillport Wiki Admin UI | Customer Administrator | 3
x | x | Assign Blog Roles in Skillport Blog Admin UI | Customer Administrator | 3
x | x | Define and Create Wiki Articles | Customer Administrator | 3
x | x | Define and Create Blogs | Customer Administrator | 3
x | x | Enable Publisher | Customer Administrator | 3
x | x | Assign custom privileges (publisher, manager, reporting) | Customer Administrator | 3
x | x | Enable Development Plans | Customer Administrator | 3
x | x | Define and set compliance settings (My Plan view) | Customer Administrator | 3
x | x | Marketing/Communication
x | x | Develop the marketing plan which should define a Value Proposition for e-Learning, S.M.A.R.T.program goals for e-learning, target audience planning as well as initial rollout communications using marketing plan on Client Community | Customer with LC | 21 |  |  |  |  | Make certain goals and measurement criteria are set
x | x | Identify the methods that will be used to achieve the marketing plan | Customer with LC | 21
x | x | Determine the purpose, form, and frequency of communications to management and participants | Customer with LC | 21
x | x | Identify who will design and develop the communication and marketing materials | Customer with LC | 21
x | x | Produce the marketing collateral | Customer with use of SkillSoft tools/templates | 14
x | x | Send "Teaser" communication out to general population letting them know that learning will take on a new look and feel in the upcoming weeks. | Customer | 28 |  |  |  |  | Sample Teaser Communication Notice to Employees on Client Community
x | x | Send email to managers reminding them of new learning resources that is coming and providing them with examples of "Lessons Learned about eLearning", "Benefits for Manager and Organization" and "Benefits for Learner". | Customer | 7 |  |  |  |  | Manager's Handout
x | x | Send notice to all employees that there is a new site for learning, with enhanced features and new course offerings. Include Quick Tips guide with communication. | Customer | 0 |  |  |  |  | Site Launch Announcement Skillport Quick Start Guide -http://documentation.skillsoft.com/skillport/platform/user_guides/sp_learner_qs_guide_7_3.doc Skillport Reporting Quick Start Guide - https://community.skillsoft.com/Products/documents/SkillPort_7_3_Reporting_Quick_Start_Guide.doc
x | x | Conduct Open House or Virtual Open House events | Customer | 7
x | x | Implementation
x | x | Schedule Kick-off Meeting | Customer | 21
x | x | Prepare Kick-off Presentation | Customer with LC/RAE | 14
x | x | Procure incentives | Customer | 14
x | x | Conduct Kick-off Meeting | Customer with LC/RAE | 0
x | x | Post-Deployment
x | x | Identify and plan for ongoing marketing efforts thorughout the program | Customer with LC | -7
x | x | Distrubute ongoing marketing communications | Customer | ongoing
x | x | Establish a program review process and schedule | Skillsoft/Customer | -28
x | x | Conduct initial program review and measurement | Skillsoft/Customer | -90 |  |  |  |  | Make certain to update any existing goals, add new ones
x | x | Establish Library Maintenance Process | LC/Customer | ongoing
x | x | Escalation procedures for post deployment technical issues - including PPM, hosting issues | Skillsoft | ongoing

## ILT
ILT Implementation Project Plan |  | Target Launch to Users Date: |  |  |  | 2013-05-30
Task/Deliverables | Responsibility | # of Days Back | Planned End Date | Day of Week | Actual End Date | Comment | Notes for LC
Planning/General
Project Kick off call | All | 57 | 2013-04-03
Review training options on Client Community | Customer | 50 | 2013-04-10
Review Admin Guide through Documentation site: http://documentation.skillsoft.com/23675.htm | Customer | 44 | 2013-04-16
Review End User Documentation through Documentation Site | Customer | 44 | 2013-04-16
Implementation Planning Call | All | 51 | 2013-04-09
Determine how ILT courses will be assigned via the Skillport catalog | LC/Customer | 37 | 2013-04-23
Reporting Requirements
Define reporting requirements | LC/Customer | 22 | 2013-05-08
Ensure group structure supports reporting requirements | LC/Customer | 22 | 2013-05-08
Define report templates | LC/Customer | 10 | 2013-05-20
ILT - Configuration Facilities, Contacts
Establish naming convention for facilities | LC/Customer | 20 | 2013-05-10
Establish naming convention for contacts | LC/Customer | 20 | 2013-05-10
Create Facilities in lit module | Customer | 15 | 2013-05-15
Create contacts in lit module | Customer | 15 | 2013-05-15
ILT - Roles
Define and Create ILT administrators | LC/Customer | 20 | 2013-05-10 |  |  | Manual or Batch
Define and Create ILT Instructors | LC/Customer | 20 | 2013-05-10 |  |  | Manual or Batch
Define ILT and Create Session Administrators | LC/Customer | 20 | 2013-05-10 |  |  | Manual or Batch
Define and Create Course Administrators | LC/Customer | 20 | 2013-05-10 |  |  | Manual or Batch
Define and Create Session Approvers | LC/Customer | 20 | 2013-05-10 |  |  | Manual or Batch
Define and Create Managers (for manager approval option) | LC/Customer | 20 | 2013-05-10 |  |  | Manual or Batch
Ensure that all parties are in SkillPort | LC/Customer | 15 | 2013-05-15
Make role assignments in ILT module | Customer | 15 | 2013-05-15
Input Managers for Manager Approval in SkillPort | Customer | 15 | 2013-05-15
ILT - Courses and Sessions
Establish naming convention for courses/sessions | LC/Customer | 20 | 2013-05-10
Create courses/sessions in ILT module | Customer | 15 | 2013-05-15 |  |  | Manual or Batch
Determine course assignments | Customer | 10 | 2013-05-20
Edit curricula assignment in SkillPort | Customer | 10 | 2013-05-20
Create learning programs in SkillPort | Customer | 10 | 2013-05-20
Complete necessary manual data entry | Customer | 8 | 2013-05-22
Marketing/Communication
Create plan for communicating ILT enrollment process to users | LC/Customer | 5 | 2013-05-24
Communicate process to end users | LC/Customer | 5 | 2013-05-24
Training
Train Administrators on system functionality by role and responsibility | Customer | 3 | 2013-05-27
Deliver customer-specific site training to instructors | Customer | 3 | 2013-05-27